Milestones

simple centered box

Date Description 2025-03-01 Choose a project proposal and send your choice via email to epsatisep@gmail.com 2025-03-15 Define the Project Backlog (what must be done and key deliverables - every member should preferably participate in every task), Global Sprint Plan, Initial Sprint Plan (which tasks should be included, who does what) and Release Gantt Chart of the project and insert them on the wiki (planning) 2025-03-12 Upload the “black box” System Diagrams & Structural Drafts to the wiki 2025-03-19 Upload the List of Components and Materials (what & quantity) to the wiki 2025-03-26 Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure 2025-04-06 Upload the Interim Report and Presentation to the wiki. The report must contain the the following chapters: Introduction, Project Management, State of the Art, Marketing Plan, Eco-efficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography. In particular, the Project Management chapter includes the updated project progress register, the sprint report for completed sprints (tasks that were included, statuses, assignees, allocations) and the updated release Gantt chart 2025-04-10 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks 2025-04-15 Upload 3D model video to the wiki 2025-04-29 Upload the final List of Materials (local providers & price, including VAT and transportation) 2025-05-02 Upload refined Interim Report (based on Teacher & Supervisor Feedback) 2025-05-14 Upload packaging solution to Deliverables and Report 2025-05-28 Upload the results of the Functional Tests to the wiki 2025-06-15 Upload the Final Report, Presentation, Video, Paper, Poster and Manual 2025-06-18 Final Presentation, Individual Discussion and Assessment (reserve the whole day) 2025-06-25 Update the wiki, report, paper with all suggested corrections Place in the files section of the MS Teams channel of your team a folder with the refined deliverables (source + PDF) together with all code and drawings produced Hand in to the EPS coordinator a printed copy of the poster, brochure and leaflet 2025-06-26 Hand in the prototype and user manual to the client Receive the EPS@ISEP certificate Bring typical food from your country

2025-03-01 Choose a project proposal and send your choice via email to epsatisep@gmail.com

2025-03-15 Define the Project Backlog (what must be done and key deliverables - every member should preferably participate in every task), Global Sprint Plan, Initial Sprint Plan (which tasks should be included, who does what) and Release Gantt Chart of the project and insert them on the wiki (planning)

2025-03-12 Upload the “black box” System Diagrams & Structural Drafts to the wiki

2025-03-19 Upload the List of Components and Materials (what & quantity) to the wiki

2025-03-26 Upload the detailed System Schematics & Structural Drawings to the wiki and do the cardboard scale model of the structure

2025-04-06 Upload the Interim Report and Presentation to the wiki. The report must contain the the following chapters: Introduction, Project Management, State of the Art, Marketing Plan, Eco-efficiency Measures for Sustainability, Ethical and Deontological Concerns, Proposed Solution and Bibliography. In particular, the Project Management chapter includes the updated project progress register, the sprint report for completed sprints (tasks that were included, statuses, assignees, allocations) and the updated release Gantt chart

2025-04-10 Interim Presentation, Discussion and Peer, Teacher and Supervisor Feedbacks

2025-04-15 Upload 3D model video to the wiki

2025-04-29 Upload the final List of Materials (local providers & price, including VAT and transportation)

2025-05-02 Upload refined Interim Report (based on Teacher & Supervisor Feedback)

2025-05-14 Upload packaging solution to Deliverables and Report

2025-05-28 Upload the results of the Functional Tests to the wiki

2025-06-15 Upload the Final Report, Presentation, Video, Paper, Poster and Manual

2025-06-18 Final Presentation, Individual Discussion and Assessment (reserve the whole day)

2025-06-25:

Update the wiki, report, paper with all suggested corrections

Place in the files section of the MS Teams channel of your team a folder with the refined deliverables (source + PDF) together with all code and drawings produced

Hand in to the EPS coordinator a printed copy of the poster, brochure and leaflet

2025-06-26:

Hand in the prototype and user manual to the client

Receive the EPS@ISEP certificate

Bring typical food from your country